| School Improvement Plan 2014 – Literacy Carrigduff NS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Baseline information - In our pupil questionnaire most pupils 85% (middle room) 73% (senior room) feel that they were good at spellings. In a parent questionnaire, most parents concurred. - Teachers report many children spell phonetically and are confident using this method. Some children have difficulty spelling using words from sight vocabulary. - All teachers report that spelling test attainment is high, however some pupils don’t use spelling skills in their general writing. - A focus group of senior class pupils reported that the high frequency words and the commonly misspelled words were more important to learn; their effort varies depending on the type of writing eg. less effort on spelling in free writing; rewards motivate children. - The focus group of parents (PTA committee December 2013) reported that most parents encourage pupils to use their word attack skills to break down spellings; parents were aware of some but would like more direction as to appropriate strategies for varying aged pupils. |  |  |  |  |
| Summary of main areas requiring improvements | - All pupils will review spellings learned to date and will improve their use of those spellings in their day to day writing. - Class teachers will include a variety of strategies in their lesson planning and be less dependent on the graded spelling scheme. - Parent Information Evenings in June / September will include direction on assisting homework and will give appropriate strategies to assist pupils working on spellings. |  |  |  |
| Improvement Targets | Required Actions | Success Criteria / Measurable Outcomes | Persons Responsible | Timeframe for Actions |
| Children need to build up a sight vocabulary for spelling and to use spellings learned in general writing. | - Use of personal spelling logbooks by pupils from 1st to 6th classes - “No excuses” list for well known spellings for all pupils - Each teacher will commit to teaching discrete spelling lessons (1 per fortnight) teaching strategies and mnemonics for difficult spellings | - Children will be observed referring to their logbooks for spellings and not repeatedly asking the class teacher - Children will refer to the “no excuses” list and will use the spellings identified correctly in written class and home work - See below | - Class and support teachers - Class teachers - Class teachers | - January to June 2014 |
| To increase the gap between the chronological age and spelling age, of most (75%) children between 2nd and 6th classes. | - Administer the Schonell Spelling test in Jan / April and June 2014 to all pupils from 2nd to 6th classes. - Specific actions as above | - At least 75% of pupils’ spelling age will improve by at least two months | - Class teachers | - January to June 2014 |
| To include direction for parents on assisting homework and give appropriate strategies to assist pupils working on spellings. | - Create a framework document giving step by step direction | - A focus group of parents will be consulted in September 2014, to evaluate the effectiveness of the framework. | - All teachers | - By May 2014 |