| School Improvement Plan for September 2014 – June 2015 (Year Two) (incorporating the areas of Literacy & Numeracy) Carrigduff NS, Bunclody, Enniscorthy, Co. Wexford |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Staff Professional Reflection on SIP 2013-14 (Year One) - Staff felt there was very good engagement with the SSE process in the 2013-14 school year, beginning with some nervousness and with an understandable fear regarding workload and volume of paperwork. The year ended with the staff feeling very positive and noting beneficial changes in all classrooms. - In September 2014 the staff engaged in review of SSE progress to date before writing this SIP 2014-15 (Year Two). On reflection the staff realised that an easily measurable target had been chosen for our first School Improvement Plan, merely because it was the most measurable of our desired improvements. However this was not the issue that staff felt was most urgent on the coalface, and consequently teachers reported that while they had made many very positive changes in the area of literacy, only minor improvements were made in the target area, spellings. As a result two of the targets from SIP One will carry over to SIP Two. - Staff reflected on how the targets for our first SIP had been chosen and based on our learning experience, we will ensure that our future targets are the most urgent and also achievable / measurable in the time frame. - The Inspectorate have organised a day conference on SSE in Malahide in September 2014. The principal will attend. The Inspectorate has offered support to schools this term. The staff have happily agreed to accept this offer to reflect and plan forward with an Inspector. |  |  |  |  |  |
| Baseline information Literacy - In our pupil questionnaire most pupils 85% (middle room) 73% (senior room) feel that they were good at spellings. In a parent questionnaire, most parents concurred. - Teachers report many children spell phonetically and are confident using this method. Some children have difficulty spelling using words from sight vocabulary. - All teachers report that spelling test attainment is high, however some pupils don’t use spelling skills in their general writing. - A focus group of senior class pupils reported that the high frequency words and the commonly misspelled words were more important to learn; their effort varies depending on the type of writing eg. less effort on spelling in free writing; rewards motivate children. - The focus group of parents (PTA committee December 2013) reported that most parents encourage pupils to use their word attack skills to break down spellings; parents were aware of some but would like more direction as to appropriate strategies for varying aged pupils. Baseline Information Numeracy - In our parent survey, parents reported the following successes in the teaching of numeracy: classroom teaching, differentiation (hidden from children), children’s attitude to maths, recall of number facts, applying maths to real life, building confidence, daily maths lessons, tables test weekly, IT support. - In our parent survey, parents reported the following areas for improvement in the teaching of numeracy: more written maths homework, applying excellent recall of number facts in problem-solving situations, pupil self and peer corrections, more practical application of maths, more feedback to parents on methods used, early contact in the event of a problem, more IT. - Attainment levels in numeracy are above national norms (in May 2014 all pupils in the school had a STen of 4 or more) - Teachers, parents and pupils agree that the standard of work in copybooks in terms of lay-out and presentation is very good, and there is a commendable focus in our school on becoming very familiar with tables / number facts. - Teachers employ a good range of active learning methodologies, including the ongoing use of ICT. - In a focus group all teachers reported a desire to use concrete material in a more organised and more frequent basis. Teachers discussed an issue around the storage of and access to central manipulatives and the need to record the manipulatives needed when planning. |  |  |  |  |  |
| Summary of main areas requiring improvements |  | - All pupils will review spellings learned to date and will improve their use of those spellings in their day to day writing. - Class teachers will include a variety of strategies in their lesson planning and be less dependent on the graded spelling scheme. - Parent Information Evenings in June / September will include direction on assisting homework and will give appropriate strategies to assist pupils working on spellings. - All teachers will compile a bank of mathematical language appropriate to each classroom and will plan for common methodologies used throughout the school. - Teachers will plan for the use of manipulatives in maths lessons. - Resources for numeracy available in the school will be inventoried. - Teachers will include targets for literacy / numeracy on planning templates to focus teachers planning. - Invite a secondary school maths teacher to inform staff about Project Maths (approaches, strategies, language etc) |  |  |  |
| Improvement Targets |  | Required Actions | Success Criteria / Measurable Outcomes | Persons Responsible | Timeframe for Actions |
| Literacy Targets (First area chosen) | Children need to build up a sight vocabulary for spelling and to use spellings learned in general writing. | - Each teacher will commit to teaching discrete spelling lessons (1 per fortnight) teaching strategies and mnemonics for difficult spellings | - See below | - Class teachers | - January to June 2015 |
|  | To increase the gap between the chronological age and spelling age, of most (75%) children between 2nd and 6th classes. | - Administer the Schonell Spelling test in Jan / April and June 2014 to all pupils from 2nd to 6th classes. - Specific actions as above | - At least 75% of pupils’ spelling age will improve by at least two months | - Class teachers | - January to June 2015 |
| Numeracy Targets (2nd Area chosen) | To improve teachers’ planning for maths | - Compile a bank of mathematical language appropriate to each classroom. - Plan for common methodologies used throughout the school. - 5/10 mins of every staff meeting to review actions to date. - Teachers will plan for the use of manipulatives in maths lessons. - Resources available in the school will be inventoried. - Include targets for literacy / numeracy on planning templates to focus teachers planning. - Invite a secondary school maths teacher to talk to staff about Project Maths (approaches, strategies, language etc) | - In an oral test to define mathematical terms 90% of pupils will successfully describe 8/10 terms. - Manipulatives will be used in all maths lessons at least twice a week. - At least one lesson in each fortnightly plan will focus on the targeted areas. | - All teachers - All teachers - All teachers - Class teachers - Janet Rothwell - Class teachers - Carolyn Good | - By December 2015 - By Easter 2016 - From September 2015 - From September 2015 - By end September 2015 - From September 2015 - By end September 2015 |